## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Needs improvement | Decrease the table tirn time more | Maor than 50% customers have to wait more than 15 minutes acc. to the servey result. | Increase the kitchen strength to prepare food more quickly.
Project team | Went well | Ticketing System | Both kitchen managers accept this in retros meeting. | Maintain this in future also.
Project team | Needs improvement | POS integration process | Restaurants consultant tell this in retros meeting | Tell the Web studio to develop updates which solve this integration issues.
Customers | Needs improvement | Birthday Club | In servey results, only 16% customers sign-up for birthday club. | Restaurants consultant working with the designer to update the content on the website
Project team | Needs improvement | Few Internal Operational Issue | Project manager tells in the meeting | Understand each location’s history before planning gets underway in next roll-out.
Project team | Needs improvement | Some vacation time needed to account in project plan | Restaurants consultant experience this while installation. | Account vacation/holiday time in project planning next time.
Project team | Needs improvement | Co-ordination problems between front and back house staff | Kitchen manager accept this in the retros meeting | Develop a more comprehensive training session, or even break the training up into two parts
Project team | Needs improvement | The Waitstaff Training process | General manager (Alex) tell this in meeting | Develop a more comprehensive training session, or even break the training up into two parts
Customers | Went well | Software navigation | 78% cutomers find ease-to-use tablet according to survey results | Bring some new features in coming future
Customers | Went well | Food deliver within 30 minutes | 86% customers get their order within 30 minutes acc. To survey results | Increase kitchen strength to attain the restaurants standards of 95%.
Customers | Needs improvement | Cash Payment | Around 18% customers not pat through tablets according to the survey results. | Update the software with cash payment option also.