## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Project Initiation
Gather some data on tablet menu service | Digital Menu |  |  | 5 days
Interview with the staffs | Try to buy-in the employees about new service. |  |  | 1 Week
Take estimates and choose tablet vendor by gathering estimates | Best uses for tablets at your restaurants |  |  | 3 Days
Determine tablet tracking software and order locking features | Gather information about tablet software |  |  | 2 Days
Research on tablet peripherals, like charging stands | Eg ; Tablet stand, Charging docks, cleaning kit, etc. |  |  | 4 Hours
Research data metrics | Figure out the success metrics of this project |  |  | 1 Day
Create Project Charter (Goals and Scope) |  |  |  | 2 Days
Schedule kick off meeting | Giving inter about this project's scope, goals and their roles. |  |  | 3 Hours
Milestone : Research about the tablet menu and other estimates
Project Planning
Research the extent of installation at each location | Deply your new restaurants |  |  | 4 Days
Choose a tablet vendor |  |  |  | 2 Days
Oversee wiring of tablets at each location | For wiring across the restaurants |  |  | 1 Day
Book Electrician |  |  |  | 3 Days
Choose tablet software package (design, layout, update) | Select the design, layout, future upodates, features, etc. |  |  | 1.5 Weeks
Book a web studio |  |  |  | 2 Days
Check the current internet service and update if necessary | Check the internet conectivity across the both restaurants |  |  | 2 Hours
Milestone : Draft the Project Planning and Milestone
Task Sourcing
Create contracts and statements of work for tablet vendor |  |  |  | 1 Day
Create tablet vendor timeline and deliverables schedule |  |  |  | 1 Day
Create contracts and statements of work for web studio |  |  |  | 1 Day
Create web studio timeline and deliverables schedule |  |  |  | 1 Day
Milestone : Draft the schedule, Sow, contracts and timelines of the vendors
Task Execution
Install Wiring across the restaurants for pilot service | Install wiring across both the restaurants |  |  | 5 days
Install tablets in the bar areas at the both restaurant | Shipped by the vendor and collected by us. |  |  | 10 Days
Install software on the tablets after wiring |  |  |  | 1 Day
Upload mockup menu content and categorize the online menus | Upload new menu, design, layout, coupons, mock-ups to database. |  |  | 4 Hours
Test run of the tabletop tablet system | Test run to confirm that everything is perfect. |  |  | 2 days
Project Plans Updates | Update your stakeholders on real-time. |  |  | Regular
Milestone : Completion of the installation of tablets and its software
Staffs Training
Develop a training plan for staff and GMs |  |  |  | 1 Week
Train GMs on new software | 2 hours of training for each GM at each locations |  |  | 2 Days
Train staff on new software by their GMs | 4 Hours of training for every staff at each location |  |  | 8 Days
Get feedback from the staff regarding the new technology | Geeting feedback about new service anf for future improvement |  |  | 2 days
Milestone : Complete the staffs training abot new service
Testing and Improvement Stage
Schedule a Family Launch Day after training | Family act as test customers to show demo of our new service. |  |  | 2 days
Gather feedback from the Launch Day | Gather feedback about our pilot srvice |  |  | 2 Hours
Implement the feedback from staffs and family | Try ti Implement It. |  |  | 5 Days
Milestone : Test the new service on selected customers
Launching a Pilot Service
Create a launch day plan |  |  |  | 1 Week
Launch the Pilot service |  |  |  | 1 Day
Restrospetive of the project | Discuss about the problems, future improvements, lessons learned, etc. |  |  | 2 Hours
Milestone : Launch the tablet menu service in two restaurants

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Gather some data on tablet menu service | Digital Menu | 5 days | 4 Days | 1 Week | 2 Weeks
Interview with the staffs | Try to buy-in the employees about new service. | 1 Week | 5 Days | 1 Week | 1.5 Weeks
Take estimates and choose tablet vendor by gathering estimates | Best uses for tablets at your restaurants | 3 Days | 2 Days | 3 Days | 5 Days | L
Determine tablet tracking software and order locking features | Gather information about tablet software | 2 Days | 1 Day | 2 Days | 3 Days | M
Research on tablet peripherals | E.g. ; Tablet stand, Charging docks, cleaning kit, etc. | 4 Hours | 3 Hours | 1 Day | 2 Days | L
Research data metrics | Figure out the success metrics of this project | 1 Day | 6 Hours | 1 Day | 2 Days
Create Project Charter (Goals and Scope) |  | 2 Days | 1 Day | 3 Days | 5 Days
Schedule kick off meeting | Giving inter about this project's scope, goals and their roles. | 3 Hours | 1.5 Hours | 2.5 Hours | 1 day
Research the extent of installation at each location | Deply your new restaurants | 4 Days | 2 Days | 4 Days | 1 Week
Choose a tablet vendor |  | 2 Days | 1 Day | 2 Days | 4 Days
Book Electrician | For wiring across the restaurants | 1 Day | 3 Hours | 6 Hours | 1 Day
Oversee wiring of tablets at each location |  | 3 Days | 2 Days | 4 Days | 1 Week
Choose tablet software package (design, layout, update) | Select the design, layout, future updates, features, etc. | 1.5 Weeks | 1 Week | 1.5 Weeks | 2 Weeks | L
Book a web studio |  | 2 Days | 6 Hours | 1 Days | 2 Days
Check the current internet service and update if necessary | Check the internet connectivity across the both restaurants | 2 Hours | 1 Hour | 2 Hours | 1 Day
Create contracts and statements of work for tablet vendor |  | 1 Day | 6 Hours | 1 Day | 2 Days
Create tablet vendor timeline and deliverables schedule |  | 1 Day | 6 Hours | 1 Day | 2 Days
Create contracts and statements of work for web studio |  | 1 Day | 6 Hours | 1 Day | 2 Days
Create web studio timeline and deliverables schedule |  | 1 Day | 6 Hours | 1 Day | 2 Days
Install Wiring across the restaurants for pilot service | Install wiring across both the restaurants | 5 days | 2 Days | 5 Days | 1 Week | M
Install tablets in the bar areas at the both restaurant | Shipped by the vendor and collected by us. | 10 Days | 8 Days | 12 Days | 2 Weeks | M
Install software on the tablets after wiring |  | 1 Day | 6 Hours | 1 Day | 2 Days
Upload mock-up menu content and categorize the online menus | Upload new menu, design, layout, coupons, mock-ups to database. | 4 Hours | 2.5 Hours | 4 Hours | 1 Day | L
Test run of the tabletop tablet system | Test run to confirm that everything is perfect. | 2 days | 10 Hours | 2 Days | 3 Days
Project Plans Updates | Update your stakeholders on real-time. | Regular | - | - | - | H
Develop a training plan for staff and GMs |  | 1 Week | 5 Days | 1 Week | 1.5 Weeks | H
Train GMs on new software | 2 hours of training for each GM at each locations | 2 Days | 1 Day | 2 days | 3 Days | H
Train staff on new software by their GMs | 4 Hours of training for every staff at each location within three days | 8 Days | 6 Days | 8 Days | 2 Weeks | L
Get feedback from the staff regarding the new technology | Geeting feedback about new service anf for future improvement | 2 days | 6 Hours | 2 Days | 4 Days | H
Schedule a Family Launch Day after training | Family act as test customers to show demo of our new service. | 2 days | 1 Day | 2 days | 3 Days
Gather feedback from the Launch Day | Gather feedback about our pilot srvice | 2 Hours | 1 Hour | 2 Hours | 1 Day
Implement the feedback from staffs and family | Try ti Implement It. | 5 Days | 3 Days | 5 Days | 1 Week | M
Create a launch day plan |  | 1 Week | 4 Days | 1 Week | 2 Weeks
Launch the Pilot service |  | 1 Day | 6 Hours | 8 Hours | 2 Days
Restrospetive of the project | Discuss about the problems, future improvements, lessons learned, etc. | 2 Hours | 1 Hour | 2 Hours | 3 Hours

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Best Uses for Tablets at Your Restaurant | Best uses for tablets at your restaurants | 2022-08-23 | Replace menus, replace register...
Best Practices for your Digital menu | Digital Menu | 2022-08-23 | Brand Menu but don't overdesign it. Categorize menu and optimize url. Add QR codes and pictures.
How to Deploy Your New Restaurant Pos Like a Pro | Deply your new restaurants | 2022-08-23 | Include staff from the start, run through and introduce troubleshooting.

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5